## Dail
| Neel |  |  | Samarth |  |  | Raviraj |  |  | Mansi
Date | Work Done | Will Do Today | Challenges | Work Done | Will Do Today | Challenges | Work Done | Will Do Today | Challenges | Work Done | Will Do Today | Challenges
2024-09-04 | Boiler Plate for Dasboard- Without Navigation | Adding Navigation | Might have to switch to Next JS, as its navigationis easier | UI Mockup Initiated | Complete UI mockups |  | Research on database schema | Database Schema created | Maybe later we need to migrate to AWS DynamoDB | Login UI on Canva | Final Signup Page UI | none
2024-10-04 | Learning Navtigation with Next JS, along with Parameters | Implement the logic on the web pages |  | UI Mockup completed | Learn React, routing |  | Understood and made the changes in order to migrate from nosql to sql | Database Schema in mysql | platform changed from mongodb to mysql |  | Started with a signup page where student, faculty and admin can log in baed on their role | pages folder was outside the src folder so to make routing easier I have chnaged the directory structure
2024-11-04 | Web Page shifted to using Next Js for Navigation, folderstructure Implemented. Completed the Boiler plate user story.Implement the UI for the first User Story (Current and Previous Courses) | Implementing the UI for grades |  | Gained some knowledge | Start with UI for Student Account |  | made the database schema in mysql | Migrate all the data to cloud so that it's accessible to everyone. | Learning how to migrate database to cloud |  | Improved the frontend as well as added a SJSU symbol in the signup page | made the webpage responsive
2024-12-04 | Started with UI for showing grades for students for current and previous semesters. Nested sidebar for each course added, overall styling changed | Completing the UI for viewing the grades |  | Made basic UI and did navigation using Page routing | Start with UI for Admin seeing courses by faculty by semester |  | Migrating database from mysql local to AWS RDS cloud | understanding the forlder structure and learning the required framework |  |  | Learning Tailwind CSS, and read a nextJS documentation, made routing to dashboards based on the roles user log in | implementing tailwind css with nextjs
13/04/24 | Completed the UI for viewing grades | Connectin UI with backend, figurig out how to pass information using state and other methods |  | Made the basic UI with navigation | Refactor the code from page routing to app routing |  | Implemented the styling of pages | making the API for data retrieval |  |  | implemented logic for routing | none
15/04/24 |  | Passing Information from one page to another using state |  | Refactored the code | Connecting backend, database and frontend |  |  | Working on NextJS |  | working with newer version of nextjs | Figure out how to implement login UI in updated code directory | none
16/04/24 |  | Passing Information from one page to another using state |  | Connections Established | Fetch the profile data and display it |  | updated the tables in database with values | Working on faculty should be able to see list of students |  | Final singup UI changes pushed in github in mansi-signup branch | setup an api-route in next.js, implement the api route handler | -
17/04/24 | Setthin Course Code and Student in localStroage, so that I can be retrived from any webpage | Develop queries for backend, for current and previous courses | Some data might be missing |  | Updating the Student information |  | Worked on this ticket: https://sjsu-neelbdesai.atlassian.net/plugins/servlet/mobile?originPath=%2Fbrowse%2FPI2-54#issue/PI2-54 also done the UI part for faculty should be able to view students | Adding a new column for database in courses table. Made a new column as per the request called date and altered the database. Removed the enum and added the date column for all rows. Also worked on faculty UI. |  | Admin UI mockup and connected database with VSCode, wrote queries for student role | Reading about flask and how to connect signup page form with backend | flask server was not getting GET method from client server
18/04/24 | Done with all queries | Developing backend that can peform the required functionalities | Need to generate synthetic data for feature demonstration | Bio, links updation not going through | Solve the errors | CORS | Done with all the queries | Developing the backend that can perform the required functionalities. |  | Connected flask server with frontend | Create student api for login page | none
19/04/24 | Backend connected to database | Connecting Backend to front end |  | Information Updation Working | Admin can look at the faculties |  | Backend connected to database | Connecting backend with frontend in order to complete the tasks. |  | wrote queries | Work on Admin UI, connect backend with frontend | none
20/04/24 | Connected front end and backend. Completed the student viewing courses and grades user stories | Done for Sprint |  | Faculty List retrieval working | retrieving courses taught by faculty in a different container |  | Connecting the front end and backend | Done for the sprint. Completed the following tasks: 1) Faculty- Courses 2) Faculty- student in courses 3) Mock Database with values |  |  | Connected backend and frontend of admin page | none
21/04/24 | [10 empty] | - | none
22/04/24 | Planning Next sprint tasks | Merging previous sprint branches |  |  |  |  | Planning for next sprint tasks |  |  |  | Merging previous sprint branches | none
23/04/24 | Decide on student id and courses for which extra data will be generated | Work with samarth to decide which , how will content of assigments and course contents be displayed |  | Accomplished | retriving people list based on courses in a different container |  | Merging of my brnach ravi with the sprint-3 branch ensuring that the code works after merge. | css for courses |  |  | Worked on database for users | none
|  |  |  | people by course by faculty done | [6 empty] | Worked on Admin frontend and CSS part | none
24/04/24 |  | Work with samarth to decide which , how will content of assigments and course contents be displayed |  | Done with the courses and people in those courses retrival | Decide on the Data to be generated for demo purposes |  | worked on css part for courses | frontend for student quiz and assignment |  |  | Merge signin code with admin features | merge conflicts
25/04/24 | Made a plan of how much data would be needed to demonstrate all features for Student | Generate 10 Students data |  | Decided on the data generation requirements | Generate data for certain courses |  | worked on frontend for student quiz and assignment | faculty frontend |  | run queries for admin feature according to the requirement | one Admin generated enough Mock data to demonstrate all feature | none
26/04/24 | Generated 10 Students data | For 10 Student enroll the in 4courses 3 in current sem and 1 in previous sem |  | generated the data | generate remaining faculty related data |  | worked on faculty frontend for quiz and assignment | backend for quiz and assignment |  | Admin UI | Admin should see lists of faculties, once click on faculties, fetched people/students enrolled in the course | none
27/04/24 | Task Completed | For 10 students for each of course they are enrolled in generate 5 Assignment records and 1 quizz record |  | accomplished | Admin should be able to assign an unassigned course to faculty |  | worked on backend for student and faculty for quiz and assignment | course content fontend |  | css and backend for admin | worked on the admin sidebar, when click on faculties- list of faculties is retrevied. | none
28/04/24 | Records generated | For each assignment and quiz for each course assign, generatea a link that will open on clicking the assiignment or qiz |  | In progress | Complete the feature |  | worked on the frontend of faculty course content | faculty backend |  | admin to be assigned feature | worked on admin feature with samarth to assign the faculty to unpublish course | none
29/04/24 |  | For each assignment and quiz for each course assign, generatea a link that will open on clicking the assiignment or qiz |  | Completed the implementation | Merging the code as sprint ends |  | worked on backend of faculty course content |  |  | admin database | updated the database for admin where i have inserted queries to add unpublish course with unassigned and assigned database | none
30/04/24 |  | Merge code from previous sprints |  |  |  |  | Merge code fom previous sprints. | working on faculty feature Faculty should be able to view list of courses taught by them in current and previous semesters |  | will generate mock data | Generated mock data for admin | none
2024-01-05 | Completed the mock data generation for students | Will work on the student should be able to see published assignments and quizzes |  | Merged the changes | Faculty should be able to post announcement |  | worked on frontend and backend of faculty should be able to view list of courses | working on Faculty should be able to see the list of students enrolled for each of its course |  | update the mock data | Based on the requirement and success criteria, I have updated the mock database for admin, where he/she can assign the non publish courses to any faculty | none
2024-02-05 | Completed Assignment and quiz section for users | Make changes to css to make the code base consistent |  | Announcement posting done | Diagram Component and Deployment |  | Task comleted | Completed the CSS and making consistent with student and faculty |  |  | Changed edit profile code for better user interaction.
2024-05-05 | Changes to CSS made | Refactor code to make enable role based api, and ofloading request verification to a seperate functioon |  | Completed the diagrams | Faculty should be able to assign and see student overall grades |  | Merge code fom previous sprints. | Completed dry run test on EC2 |  | merge the code | merging my branch with Samarth's branch | conflicts with css files
2024-06-05 | Refactoring in Progress | Work on Student should be able to view content of published course |  | Implementation accomplished | Testing |  | completed dry run test on cloud | Completed the deployment diagram |  | Final merging with others branch | Updated Admin and Faculty CSS and updated my branch with other features through a merge
2024-07-05 | User story completed | Testing and CSS changes |  | Everything is working as expected |  |  | deployed the final version on ec2 with load balancer | Presentation day all documentation |  | Will start with documentation | Discussion with team members on XP Values used during the project

## Sprint 1
Story | Owner | Status at End of Sprint | Reason
A student should be able to see the courses they have enrolled in current and previous sem | Neel | Moved to Next Sprint | UI Done. Was new to react and Next JS so took a great amount of time tolearn how to make a webpage.
Students should be able to view their own score for their enrolled subjects | Neel | Moved to Next Sprint
Greate Generalized UI BoilerPlate that can be used for the first page for everone | Neel | Done
Login Page | Mansi | Moved to Next Sprint | Had issues connecting with backend because had to learn about working with flask.
Admin should be able to view the list of students enrolled in a particular course | Mansi | Moved to Next Sprint | Was updating Admin Database based on the UI requirements.
Deploy the database on a Cloud patflorm | Raviraj | Done
Build a Mock database that has data from students, faculty and courses | Raviraj | Moved to Next Sprint
Faculty should be able to see the list of students enrolled for each of its course | Raviraj | Moved to Next Sprint
Faculty should be able to view list of courses taught by them in current and previous semesters | Raviraj | Moved to Next Sprint
Students should be able set profile information | Samarth | Moved to Next Sprint
Admin should be able to see course taught by faculty in the current and previous semsester | Samarth | Moved to Next Sprint

## Sprint 2
Story | Owner | Status at End of Sprint
A student should be able to see the courses they have enrolled in current and previous sem | Neel | Done
Students should be able to view their own score for their enrolled subjects | Neel | Done
Greate Generalized UI BoilerPlate that can be used for the first page for everone | Neel | Done
Login Page | Mansi | Done
Admin should be able to view the list of students enrolled in a particular course | Mansi | Done
Deploy the database on a Cloud patflorm | Raviraj | Done
Build a Mock database that has data from students, faculty and courses | Raviraj | Done
Faculty should be able to see the list of students enrolled for each of its course | Raviraj | Done
Faculty should be able to view list of courses taught by them in current and previous semesters | Raviraj | Done
Students should be able set profile information | Samarth | Done
Admin should be able to see course taught by faculty in the current and previous semsester | Samarth | Done

## Sprint 3
Story | Owner | Status at end of Sprint
A student should be able to see the content of all the courses published | Neel | Moved to next sprint
For one student generate enough mock data to demonstrate all feature | Neel | Moved to next sprint
A student should be able to see the published assignments and quizzes for a course | Neel | Moved to next sprint
After Login Page is implemented, integrate it with rest | Mansi | Moved to next sprint
For One faculty generate enough Mock data to demonstrate all features | Samarth | Moved to next sprint
For one Admin generate enough Mock data to demonstrate all features | Mansi | Moved to next sprint
Faculty should be able to post announcements | Samarth | Moved to next sprint
Faculty Should be able to add Assignments and Quizes | Raviraj | Done
Faculty should be able to add content to syllabus section of a course | Raviraj | Moved to next sprint
Merge all features together | Unassigned | Moved to next sprint
Make Faculty and Course Card CSS consistent with student | Raviraj | Moved to next sprint

## Sprint 4
Story | Owner | Status at end of Sprint
For One faculty generate enough Mock data to demonstrate all features | Samarth | Done
PI2-37 Faculty should be able to post announcements | Samarth | Done
PI2-58 For one Admin generate enough Mock data to demonstrate all features | Mansi | Done
PI2-24 A student should be able to see the published assignments and quizzes for a course | Neel | Done
PI2-57 After Login Page is implemented, integrate it with rest | Mansi | Done
PI2-23 A student should be able to see the content of all the courses published | Neel | Done
PI2-55 For one student generate enough mock data to demonstrate all feature | Neel | Done
PI2-32 Faculty should be able to add content to syllabus section of a course | Samarth | Done
PI2-65 Make Faculty and Course Card CSS consistent with student | Raviraj | Done
PI2-64 Merge all features together | Raviraj | Done
PI2-28 Admin Should be able assign a new course to a faculty member for current semester | Samarth | Done
PI2-34 Faculty Should be able to view the grades of each student, for each course that have taught | Mansi | Done
PI2-31 Current courses will include Published and Unpublished courses | Mansi | Done
PI2-35 Faculty should be able to assign grades to students enrolled in their course | Samarth | Done
PI2-40 Deploy Web App on AWS EC2 with Auto Scaled EC2 cluster and Load balancer | Raviraj | Moved to next sprint
PI2-45 Weekly Scrum Report | Neel | Moved to next sprint
PI2-61 UML Component Diagram | Samarth | Moved to next sprint
PI2-62 UML Deployment Diagram | Raviraj | Moved to next sprint
PI2-26 Students should be able set profile information | Samarth | Done

## Sprint 5
Story | Owner | Status at end of Sprint
PI2-40 Deploy Web App on AWS EC2 with Auto Scaled EC2 cluster and Load balancer | Raviraj | Done
PI2-45 Weekly Scrum Report | Neel | Done
PI2-61 UML Component Diagram | Samarth | Done
PI2-62 UML Deployment Diagram | Raviraj | Done